## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27 | 2016-02-28 | 2016-02-29
Just copy a row to make a new one |  | Total person hours | 39.5 | 39.5 | 39.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5
|  | Ideal Person Hours | 39.5 | 33.8571 | 28.2143 | 22.5714 | 16.9286 | 11.2857 | 5.6429 | 0 | Totals
Term Paper | Read and note paper | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Peter | 13.5
Term Paper | Read and note paper | Daniela | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Jennifer | 13
Term Paper | Read and note paper | Jennifer | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Daniela | 11
Issue 1 | Document findings | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Document findings | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 3 | Document findings | Peter | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
HW2 | Do HW2 | Daniela | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11
HW2 | Do HW2 | Jennifer | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11
HW2 | Do HW2 | Peter | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Continuing work on HW2 HW2 is larger than initially planned by an order of magnitude Paper selection finalized, going to start making notes and doing supplemental research Project is on hold until other work is done

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days