## Burn Down Chart
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2014-02-05 | 2014-02-06 | 2014-02-07 | 2014-02-08 | 2014-02-10 | 2014-02-11 | 2014-02-12
All Priortized tasks (abstract level) of complete project | Analyzing Strategy for Categorization of 044_Hosting, Api's work , Documentation | Member1 | 8*7=56 | 7 | 7 | 7 | 6 | 4
Task a | Sofie Disambiguation work, algorithm understanding | Member2 | 8*7=56 |  | 7 | 7 | 7 | 7
Task b | Analyzing Strategy for Categorization of 048_IT | Member3 | 8*7=56 | 6 | 4 | 4 | 7 | 7
Task c | Analyzing Strategy for Categorization of 043_Sports | Member4 | 8*7=56 | 7 | 6 | 6 | 7 | 5
Task .. | Analyzing Strategy for Categorization of 034_Education | Member5 | 8*7=56 | 7 | 7 | 7 | 7 | 1
Task .. | Analyzing Strategy for Categorization of 010_Entertainment | Member6 | 8*7=56 | 4 | 6 | 6 | 7 | 1
Task ..
Task N |  | Total person hours | 336 | 305 | 268 | 231 | 190 | 165 | 165 | 165
|  | Days | Hours Remaining
|  | 0 | 305
268
231
NOTE: The burndown chart shows what has been achieved so far up to Day 4 of |  |  | 190
165
Sprint task are added in planning meeting but can be added later on with consensus of all team members |  |  | 165
165
#REF!
#REF!

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member4 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 043_Swimsuits_Lingerie | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member5 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 034_Education | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member6 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 010_Entertainment | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days