## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-06 | 2016-02-07 | 2016-02-08
Just copy a row to make a new one |  | Total person hours | 24 | 24 | 24 | 24 | 24 | 24 | 23.5 | 23.5
|  | Ideal Person Hours | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0 | Totals
Term Paper | Pick a Paper | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | Peter | 9
Term Paper | Pick a Paper | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Jennifer | 7
Term Paper | Pick a Paper | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Daniela | 7
Term Paper | Coordinate Papers | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 1 | Research WebGL | Daniela | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Issue 1 | Draw some lines and circles | Daniela | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 1 | Document findings | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Research WebSockets | Jennifer | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Issue 2 | Implement a simple client | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Implement a simple server | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Document findings | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 3 | Research SpringBoot | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 3 | Create simple application | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 3 | Document findings | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days