## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14
Just copy a row to make a new one |  | Total person hours | 28 | 28 | 28 | 28 | 28 | 28 | 22 | 22
|  | Ideal Person Hours | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | Totals
Term Paper | Write initial draft section | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Peter | 10
Term Paper | Write initial draft section | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Jennifer | 9
Term Paper | Write initial draft section | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Daniela | 8
Term Paper | Create initial draft | Peter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Term Paper | Create initial draft | Daniela | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Term Paper | Create initial draft | Jennifer | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
HW3 | HW3 - Initial + Logging + Error Handling | Peter | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3
HW3 | HW3 - Databasing | Daniela | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3
HW3 | HW3 - Home page | Jennifer | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Plan to have paper initial draft done this week. Shifting Project work to out of scope for now. Shifted focus from paper to HW3 to meet closer deadline

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days