## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-06 | 2016-02-07 | 2016-02-08
Just copy a row to make a new one |  | Total person hours | 24 | 24 | 24 | 24 | 23.5 | 21.5 | 22 | 22
|  | Ideal Person Hours | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0 | Totals
Term Paper | Pick a Paper | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | Peter | 9
Term Paper | Pick a Paper | Daniela | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | Jennifer | 7
Term Paper | Pick a Paper | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Daniela | 7
Term Paper | Coordinate Papers | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 1 | Research WebGL | Daniela | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2
Issue 1 | Draw some lines and circles | Daniela | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 1 | Document findings | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Research WebSockets | Jennifer | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4
Issue 2 | Implement a simple client | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Implement a simple server | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Document findings | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 3 | Research SpringBoot | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 3 | Create simple application | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 3 | Document findings | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Team ended up catching the flu-like bug over the weekend and little work actually got done. Going to carry over objectives from this sprint to next sprint and do some weekend meetup time to catch up.

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days