## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04 | 2016-03-05 | 2016-03-06 | 2016-03-07
Just copy a row to make a new one |  | Total person hours | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 6.5 | 5.5
|  | Ideal Person Hours | 9.5 | 8.1429 | 6.7857 | 5.4286 | 4.0714 | 2.7143 | 1.3571 | -2.2204e-15 | Totals
Term Paper | Read and note paper | Peter | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | Peter | 3.5
Term Paper | Read and note paper | Daniela | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | Jennifer | 3
Term Paper | Read and note paper | Jennifer | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | Daniela | 1
Issue 1 | Document findings | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Document findings | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 3 | Document findings | Peter | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
HW2 ate a lot of the last iteration. Going to try to focus on getting a draft of the paper done. Got some work done on paper, plan to have initial draft done during next iteration

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days