## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14
Just copy a row to make a new one |  | Total person hours | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  | Ideal Person Hours | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | -2.2204e-15 | Totals
Term Paper | Write initial draft section | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Peter | 5
Term Paper | Write initial draft section | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Jennifer | 4
Term Paper | Write initial draft section | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Daniela | 3
Term Paper | Create initial draft | Peter | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Term Paper | Create initial draft | Daniela | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Term Paper | Create initial draft | Jennifer | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Plan to have paper initial draft done this week. Shifting Project work to out of scope for now.

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days