## Overview
Product backlog item | Sprint Task | Resource Name | Initial Estimate of Efforts | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22
Just copy a row to make a new one |  | Total person hours | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5 | 36.5
|  | Ideal Person Hours | 36.5 | 31.2857 | 26.0714 | 20.8571 | 15.6429 | 10.4286 | 5.2143 | 0 | Totals
Term Paper | Pick a Paper | Peter | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Peter | 11
Term Paper | Pick a Paper | Daniela | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Jennifer | 13
Term Paper | Pick a Paper | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Daniela | 12
Term Paper | Coordinate Papers | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 1 | Research WebGL | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 1 | Draw some lines and circles | Daniela | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Issue 1 | Document findings | Daniela | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Research WebSockets | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Implement a simple client | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Implement a simple server | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 2 | Document findings | Jennifer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Issue 3 | Document findings | Peter | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
HW2 | Do HW2 | Daniela | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
HW2 | Do HW2 | Jennifer | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
HW2 | Do HW2 | Peter | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Team | Assist | Peter | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Wrapped up some stuff from Sprint 1 in Sprint 2, carrying over to Sprint 3. Not pulling in new work, due to previous performance and mid-term season. Added HW2 after initial planning

## Member1 Sprint
Tasks | Day(s)
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 044_Hosting | 14
Possible DTS Facts Construction | 7
Testing | 7
Api's work for linux and Windows | 14
Documentation Review | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## Member 2 Sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Sofie Code, Disambiguation Algorithm | 21
Extract the algorithm uses by sofie | 14
Analyze sofie compatibility with the yago2s. | 14
Testing | 7
Total Hours: | 56
Total Days: | 56/7 = 8 days

## member3 sprint
Start Date of Sprint is: 5/27/2013 to 6/04/2013
Tasks | Hours
Analyzing Strategy for Categorization of 048_IT | 21
Possible DTS Facts Construction | 14
Analyzing Keywords and hrefs Manually | 7
Testing | 14
Total Hours: | 56
Total Days: | 56/7 = 8 days